## 📊 Summary
🌍 TALKIN — DEVELOPMENT WORKMAP ¦ MASTER SUMMARY
API (Laravel) • Frontend Dashboard (React+TS) • APK (Flutter) ¦ Project: Talkin Global Multilingual Platform
| Layer | Total Tasks | ✅ Done | 🔄 In Progress | 🔲 Pending | ⛔ Blocked | Est. Days
🔧 | API Development (Laravel) | 140 | 10 | 2 | 128 | 0 | 87
🖥️ | Frontend Dashboard (React + TS) | 85 | 3 | 1 | 81 | 0 | 71
📱 | APK Dev — Android + iOS (Flutter) | 86 | 3 | 1 | 82 | 0 | 88
| TOTAL | 311 | 16 | 4 | 291 | 0 | 246
STATUS GUIDE
✅ Done | Task complete and verified
🔄 In Progress | Currently being developed
🔲 Pending | Not yet started
⛔ Blocked | Waiting on dependency / decision
🧪 Testing | Dev done — in QA/testing phase
🚀 Deployed | Live on staging or production
TASK SIZE GUIDE
S | Small — under 4 hours
M | Medium — ~1 day
L | Large — 2–3 days
XL | Extra Large — 4+ days
COLUMN GUIDE
Dev Status | Current development progress of the task
Test Status | QA / testing phase status — updated by QA team
Git Upload | Whether the task branch has been pushed to GitHub (PR created)
Assigned To | Engineer responsible for this task
Est. Days | Estimated working days (not calendar days)

## 🔧 API Development
🌍 TALKIN — API DEVELOPMENT WORKMAP
Laravel REST API ¦ Backend Engineer Tracker ¦ Talkin Platform v1.0
STATUS LEGEND → ✅ Done 🔄 In Progress 🔲 Pending ⛔ Blocked 🧪 Testing 🚀 Deployed SIZE → S = Small (<4h) M = Medium (1d) L = Large (2-3d) XL = Extra Large (4+d)
# | Task / Endpoint | Size | Priority | Dev Status | Test Status | Git Upload | Assigned To | Est. Days | Notes
⚙️ PHASE 0 — FOUNDATION & SETUP
1 | Project init: Laravel 11 + Sanctum install | S | 🔴 Critical | ✅ Done | ✅ Done | ✅ Done | Backend Dev | 0.5
2 | Database config: MySQL + Redis connection | S | 🔴 Critical | ✅ Done | ✅ Done | ✅ Done | Backend Dev | 0.5
3 | S3 / MinIO storage config | S | 🔴 Critical | ✅ Done | ✅ Done | ✅ Done | Backend Dev | 0.5
4 | Base API response structure (success/error wrapper) | S | 🔴 Critical | ✅ Done | ✅ Done | ✅ Done | Backend Dev | 0.5
5 | ForceJsonResponse middleware | S | 🔴 Critical | ✅ Done | ✅ Done | ✅ Done | Backend Dev | 0.5
6 | Rate limiting middleware setup | S | 🔴 Critical | ✅ Done | ✅ Done | ✅ Done | Backend Dev | 0.5
7 | CORS config & env setup | S | 🔴 Critical | ✅ Done | ✅ Done | ✅ Done | Backend Dev | 0.5
8 | Seed: languages table (180+ languages) | M | 🔴 Critical | ✅ Done | ✅ Done | ✅ Done | Backend Dev | 1
9 | Seed: gifts table (initial cultural gifts) | S | 🟡 High | 🔲 Pending | 🔲 Pending | 🔲 Pending | Backend Dev | 0.5
10 | CI/CD pipeline (GitHub Actions) | M | 🟡 High | 🔲 Pending | 🔲 Pending | 🔲 Pending | DevOps | 1
🔐 AUTH MODULE — /api/v1/auth
11 | POST /auth/register — email + password | M | 🔴 Critical | 🔄 In Progress | 🔲 Pending | 🔲 Pending | Backend Dev | 1 | Validation, hash pw, send verify email
12 | POST /auth/login — JWT token issue | M | 🔴 Critical | 🔄 In Progress | 🔲 Pending | 🔲 Pending | Backend Dev | 1
13 | POST /auth/logout — token revoke | S | 🔴 Critical | 🔲 Pending | 🔲 Pending | 🔲 Pending | Backend Dev | 0.5 | Redis blacklist
14 | POST /auth/refresh — token refresh | S | 🔴 Critical | 🔲 Pending | 🔲 Pending | 🔲 Pending | Backend Dev | 0.5
15 | POST /auth/forgot-password | S | 🟡 High | 🔲 Pending | 🔲 Pending | 🔲 Pending | Backend Dev | 0.5
16 | POST /auth/reset-password | S | 🟡 High | 🔲 Pending | 🔲 Pending | 🔲 Pending | Backend Dev | 0.5
17 | GET /auth/verify-email/{token} | S | 🟡 High | 🔲 Pending | 🔲 Pending | 🔲 Pending | Backend Dev | 0.5
18 | POST /auth/social/google — OAuth | M | 🟡 High | 🔲 Pending | 🔲 Pending | 🔲 Pending | Backend Dev | 1
19 | POST /auth/social/apple — Sign In | M | 🟢 Medium | 🔲 Pending | 🔲 Pending | 🔲 Pending | Backend Dev | 1
20 | CheckRole middleware (user/admin/super_admin) | S | 🔴 Critical | 🔲 Pending | 🔲 Pending | 🔲 Pending | Backend Dev | 0.5 | RBAC
21 | CheckSuperAdmin middleware | S | 🔴 Critical | 🔲 Pending | 🔲 Pending | 🔲 Pending | Backend Dev | 0.5
👤 USER MODULE — /api/v1/users
22 | GET /users/me | S | 🔴 Critical | 🔲 Pending | 🔲 Pending | 🔲 Pending | Backend Dev | 0.5
23 | PUT /users/me — update account | S | 🔴 Critical | 🔲 Pending | 🔲 Pending | 🔲 Pending | Backend Dev | 0.5
24 | GET /users/{id} — public profile | S | 🔴 Critical | 🔲 Pending | 🔲 Pending | 🔲 Pending | Backend Dev | 0.5
25 | GET /users/search?q= — user search | M | 🟡 High | 🔲 Pending | 🔲 Pending | 🔲 Pending | Backend Dev | 1 | Full-text search
26 | POST /users/{id}/block | S | 🟡 High | 🔲 Pending | 🔲 Pending | 🔲 Pending | Backend Dev | 0.5
27 | DELETE /users/{id}/block | S | 🟡 High | 🔲 Pending | 🔲 Pending | 🔲 Pending | Backend Dev | 0.5
28 | POST /users/{id}/follow | S | 🟡 High | 🔲 Pending | 🔲 Pending | 🔲 Pending | Backend Dev | 0.5
29 | DELETE /users/{id}/follow | S | 🟡 High | 🔲 Pending | 🔲 Pending | 🔲 Pending | Backend Dev | 0.5
30 | GET /users/{id}/followers | S | 🟢 Medium | 🔲 Pending | 🔲 Pending | 🔲 Pending | Backend Dev | 0.5
31 | GET /users/{id}/following | S | 🟢 Medium | 🔲 Pending | 🔲 Pending | 🔲 Pending | Backend Dev | 0.5
🪪 PROFILE MODULE — /api/v1/profiles
32 | GET /profiles/me | S | 🔴 Critical | 🔲 Pending | 🔲 Pending | 🔲 Pending | Backend Dev | 0.5
33 | PUT /profiles/me — update profile | M | 🔴 Critical | 🔲 Pending | 🔲 Pending | 🔲 Pending | Backend Dev | 1 | Cultural interests, bio, gender
34 | POST /profiles/me/photo — avatar upload to S3 | M | 🟡 High | 🔲 Pending | 🔲 Pending | 🔲 Pending | Backend Dev | 1
35 | PUT /profiles/me/languages | S | 🔴 Critical | 🔲 Pending | 🔲 Pending | 🔲 Pending | Backend Dev | 0.5 | native + learning
36 | PUT /profiles/me/interests | S | 🟡 High | 🔲 Pending | 🔲 Pending | 🔲 Pending | Backend Dev | 0.5
37 | GET /profiles/{id} | S | 🟡 High | 🔲 Pending | 🔲 Pending | 🔲 Pending | Backend Dev | 0.5
💬 CHAT MODULE — /api/v1/chat
38 | GET /chat/conversations — list all | M | 🔴 Critical | 🔲 Pending | 🔲 Pending | 🔲 Pending | Backend Dev | 1 | paginated
39 | POST /chat/conversations — create | M | 🔴 Critical | 🔲 Pending | 🔲 Pending | 🔲 Pending | Backend Dev | 1 | direct + group
40 | GET /chat/conversations/{id} | S | 🔴 Critical | 🔲 Pending | 🔲 Pending | 🔲 Pending | Backend Dev | 0.5
41 | GET /chat/conversations/{id}/messages — paginated | M | 🔴 Critical | 🔲 Pending | 🔲 Pending | 🔲 Pending | Backend Dev | 1 | cursor-based pagination
42 | POST /chat/conversations/{id}/messages — send | L | 🔴 Critical | 🔲 Pending | 🔲 Pending | 🔲 Pending | Backend Dev | 2 | text/image/video/audio, E2EE
43 | DELETE /chat/messages/{id} | S | 🟡 High | 🔲 Pending | 🔲 Pending | 🔲 Pending | Backend Dev | 0.5
44 | POST /chat/conversations/{id}/read — mark read | S | 🟡 High | 🔲 Pending | 🔲 Pending | 🔲 Pending | Backend Dev | 0.5
45 | POST /chat/conversations/{id}/media — upload | M | 🟡 High | 🔲 Pending | 🔲 Pending | 🔲 Pending | Backend Dev | 1 | S3 upload + signed URL
46 | POST /chat/groups — create group | M | 🟡 High | 🔲 Pending | 🔲 Pending | 🔲 Pending | Backend Dev | 1
47 | POST /chat/groups/{id}/members — add member | S | 🟡 High | 🔲 Pending | 🔲 Pending | 🔲 Pending | Backend Dev | 0.5
48 | DELETE /chat/groups/{id}/members/{userId} | S | 🟡 High | 🔲 Pending | 🔲 Pending | 🔲 Pending | Backend Dev | 0.5
49 | POST /chat/groups/{id}/leave | S | 🟢 Medium | 🔲 Pending | 🔲 Pending | 🔲 Pending | Backend Dev | 0.5
50 | WebSocket: private-chat.{id} channel setup | L | 🔴 Critical | 🔲 Pending | 🔲 Pending | 🔲 Pending | Backend Dev | 2 | Laravel Echo broadcast
📞 CALL MODULE — /api/v1/calls
51 | POST /calls/initiate — start audio call | L | 🔴 Critical | 🔲 Pending | 🔲 Pending | 🔲 Pending | Backend Dev | 2 | TURN credential issue
52 | POST /calls/{id}/answer | M | 🔴 Critical | 🔲 Pending | 🔲 Pending | 🔲 Pending | Backend Dev | 1
53 | POST /calls/{id}/decline | S | 🔴 Critical | 🔲 Pending | 🔲 Pending | 🔲 Pending | Backend Dev | 0.5
54 | POST /calls/{id}/end | S | 🔴 Critical | 🔲 Pending | 🔲 Pending | 🔲 Pending | Backend Dev | 0.5 | compute duration
55 | POST /calls/{id}/ice-candidate | M | 🔴 Critical | 🔲 Pending | 🔲 Pending | 🔲 Pending | Backend Dev | 1 | WebRTC signaling relay
56 | GET /calls/history | S | 🟡 High | 🔲 Pending | 🔲 Pending | 🔲 Pending | Backend Dev | 0.5
57 | WebSocket: call.incoming / call.ended events | L | 🔴 Critical | 🔲 Pending | 🔲 Pending | 🔲 Pending | Backend Dev | 2
🎥 VIDEO CALL MODULE — /api/v1/video
58 | POST /video/initiate | L | 🔴 Critical | 🔲 Pending | 🔲 Pending | 🔲 Pending | Backend Dev | 2
59 | POST /video/{id}/answer | M | 🔴 Critical | 🔲 Pending | 🔲 Pending | 🔲 Pending | Backend Dev | 1
60 | POST /video/{id}/decline | S | 🔴 Critical | 🔲 Pending | 🔲 Pending | 🔲 Pending | Backend Dev | 0.5
61 | POST /video/{id}/end | S | 🔴 Critical | 🔲 Pending | 🔲 Pending | 🔲 Pending | Backend Dev | 0.5
62 | POST /video/{id}/ice-candidate | M | 🔴 Critical | 🔲 Pending | 🔲 Pending | 🔲 Pending | Backend Dev | 1
63 | POST /video/{id}/toggle-video | S | 🟡 High | 🔲 Pending | 🔲 Pending | 🔲 Pending | Backend Dev | 0.5 | broadcast toggle event
64 | GET /video/history | S | 🟢 Medium | 🔲 Pending | 🔲 Pending | 🔲 Pending | Backend Dev | 0.5
🎙️ VOICE ROOM MODULE — /api/v1/rooms
65 | GET /rooms — list public rooms | M | 🔴 Critical | 🔲 Pending | 🔲 Pending | 🔲 Pending | Backend Dev | 1 | filter: language, mode
66 | POST /rooms — create room | M | 🔴 Critical | 🔲 Pending | 🔲 Pending | 🔲 Pending | Backend Dev | 1
67 | GET /rooms/{id} | S | 🔴 Critical | 🔲 Pending | 🔲 Pending | 🔲 Pending | Backend Dev | 0.5
68 | PUT /rooms/{id} — update room settings | S | 🟡 High | 🔲 Pending | 🔲 Pending | 🔲 Pending | Backend Dev | 0.5 | host only
69 | DELETE /rooms/{id} — close room | S | 🟡 High | 🔲 Pending | 🔲 Pending | 🔲 Pending | Backend Dev | 0.5
70 | POST /rooms/{id}/join — join as audience | M | 🔴 Critical | 🔲 Pending | 🔲 Pending | 🔲 Pending | Backend Dev | 1 | max capacity check
71 | POST /rooms/{id}/leave | S | 🔴 Critical | 🔲 Pending | 🔲 Pending | 🔲 Pending | Backend Dev | 0.5
72 | POST /rooms/{id}/speak — request to speak | S | 🟡 High | 🔲 Pending | 🔲 Pending | 🔲 Pending | Backend Dev | 0.5 | raise hand
73 | POST /rooms/{id}/speakers/{userId} — promote | S | 🟡 High | 🔲 Pending | 🔲 Pending | 🔲 Pending | Backend Dev | 0.5
74 | DELETE /rooms/{id}/speakers/{userId} — demote | S | 🟡 High | 🔲 Pending | 🔲 Pending | 🔲 Pending | Backend Dev | 0.5
75 | POST /rooms/{id}/cohosts/{userId} | S | 🟡 High | 🔲 Pending | 🔲 Pending | 🔲 Pending | Backend Dev | 0.5
76 | DELETE /rooms/{id}/cohosts/{userId} | S | 🟢 Medium | 🔲 Pending | 🔲 Pending | 🔲 Pending | Backend Dev | 0.5
77 | POST /rooms/{id}/kick/{userId} | S | 🟡 High | 🔲 Pending | 🔲 Pending | 🔲 Pending | Backend Dev | 0.5
78 | POST /rooms/{id}/reactions — broadcast emoji | S | 🟢 Medium | 🔲 Pending | 🔲 Pending | 🔲 Pending | Backend Dev | 0.5 | WebSocket broadcast
📰 FEED & POST MODULE — /api/v1/posts
79 | GET /posts — feed (paginated + algorithm) | L | 🔴 Critical | 🔲 Pending | 🔲 Pending | 🔲 Pending | Backend Dev | 3 | follow-based + discovery
80 | POST /posts — create post | M | 🔴 Critical | 🔲 Pending | 🔲 Pending | 🔲 Pending | Backend Dev | 1 | text/photo/video/language
81 | GET /posts/{id} | S | 🔴 Critical | 🔲 Pending | 🔲 Pending | 🔲 Pending | Backend Dev | 0.5
82 | PUT /posts/{id} — edit own post | S | 🟡 High | 🔲 Pending | 🔲 Pending | 🔲 Pending | Backend Dev | 0.5
83 | DELETE /posts/{id} | S | 🟡 High | 🔲 Pending | 🔲 Pending | 🔲 Pending | Backend Dev | 0.5
84 | POST /posts/{id}/like | S | 🟡 High | 🔲 Pending | 🔲 Pending | 🔲 Pending | Backend Dev | 0.5 | polymorphic likes
85 | DELETE /posts/{id}/like | S | 🟡 High | 🔲 Pending | 🔲 Pending | 🔲 Pending | Backend Dev | 0.5
86 | POST /posts/{id}/save | S | 🟢 Medium | 🔲 Pending | 🔲 Pending | 🔲 Pending | Backend Dev | 0.5
87 | GET /posts/saved | S | 🟢 Medium | 🔲 Pending | 🔲 Pending | 🔲 Pending | Backend Dev | 0.5
88 | GET /posts/{id}/comments | S | 🟡 High | 🔲 Pending | 🔲 Pending | 🔲 Pending | Backend Dev | 0.5 | paginated
89 | POST /posts/{id}/comments | S | 🟡 High | 🔲 Pending | 🔲 Pending | 🔲 Pending | Backend Dev | 0.5
90 | DELETE /comments/{id} | S | 🟡 High | 🔲 Pending | 🔲 Pending | 🔲 Pending | Backend Dev | 0.5
91 | Country-based discussion topics endpoint | M | 🟡 High | 🔲 Pending | 🔲 Pending | 🔲 Pending | Backend Dev | 1 | group posts by country
🎁 GIFT MODULE — /api/v1/gifts
92 | GET /gifts — catalog | S | 🟡 High | 🔲 Pending | 🔲 Pending | 🔲 Pending | Backend Dev | 0.5
93 | POST /gifts/send — send gift | M | 🟡 High | 🔲 Pending | 🔲 Pending | 🔲 Pending | Backend Dev | 1 | deduct coins, broadcast animation
94 | GET /gifts/history | S | 🟢 Medium | 🔲 Pending | 🔲 Pending | 🔲 Pending | Backend Dev | 0.5
95 | GET /gifts/leaderboard | S | 🟢 Medium | 🔲 Pending | 🔲 Pending | 🔲 Pending | Backend Dev | 0.5
96 | GET /gifts/coins/balance | S | 🟡 High | 🔲 Pending | 🔲 Pending | 🔲 Pending | Backend Dev | 0.5
97 | POST /gifts/coins/topup — payment gateway | L | 🟡 High | 🔲 Pending | 🔲 Pending | 🔲 Pending | Backend Dev | 3 | Stripe / payment integration
🌐 TRANSLATION MODULE — /api/v1/translations
98 | GET /translations/message/{id}?lang= — translate msg | M | 🔴 Critical | 🔲 Pending | 🔲 Pending | 🔲 Pending | Backend Dev | 1 | cache result in DB
99 | GET /translations/post/{id}?lang= | M | 🟡 High | 🔲 Pending | 🔲 Pending | 🔲 Pending | Backend Dev | 1
100 | POST /translations/text — arbitrary text translate | M | 🟡 High | 🔲 Pending | 🔲 Pending | 🔲 Pending | Backend Dev | 1
101 | GET /translations/languages — supported list | S | 🟡 High | 🔲 Pending | 🔲 Pending | 🔲 Pending | Backend Dev | 0.5
102 | TranslationService: Google Translate API integration | L | 🔴 Critical | 🔲 Pending | 🔲 Pending | 🔲 Pending | Backend Dev | 2
103 | TranslateMessage background job | M | 🔴 Critical | 🔲 Pending | 🔲 Pending | 🔲 Pending | Backend Dev | 1 | queue worker
🤖 MATCHING MODULE — /api/v1/matching
104 | GET /matching/preferences | S | 🟡 High | 🔲 Pending | 🔲 Pending | 🔲 Pending | Backend Dev | 0.5
105 | PUT /matching/preferences | S | 🟡 High | 🔲 Pending | 🔲 Pending | 🔲 Pending | Backend Dev | 0.5 | language, goals, cultural interests
106 | GET /matching/suggestions — top matches | M | 🟡 High | 🔲 Pending | 🔲 Pending | 🔲 Pending | Backend Dev | 1 | score >= 50
107 | POST /matching/accept/{userId} | S | 🟡 High | 🔲 Pending | 🔲 Pending | 🔲 Pending | Backend Dev | 0.5 | auto-create conversation
108 | POST /matching/decline/{userId} | S | 🟡 High | 🔲 Pending | 🔲 Pending | 🔲 Pending | Backend Dev | 0.5 | 30-day cooldown
109 | GET /matching/matches — active matches | S | 🟡 High | 🔲 Pending | 🔲 Pending | 🔲 Pending | Backend Dev | 0.5
110 | MatchingService: scoring algorithm (7 factors) | XL | 🟡 High | 🔲 Pending | 🔲 Pending | 🔲 Pending | Backend Dev | 4 | language, exchange, interests, culture, activity, goal, region
111 | RunMatchingAlgorithm scheduled job (daily) | M | 🟡 High | 🔲 Pending | 🔲 Pending | 🔲 Pending | Backend Dev | 1 | Laravel cron
🔔 NOTIFICATION MODULE — /api/v1/notifications
112 | GET /notifications — all notifications | S | 🟡 High | 🔲 Pending | 🔲 Pending | 🔲 Pending | Backend Dev | 0.5 | paginated
113 | POST /notifications/{id}/read | S | 🟡 High | 🔲 Pending | 🔲 Pending | 🔲 Pending | Backend Dev | 0.5
114 | POST /notifications/read-all | S | 🟢 Medium | 🔲 Pending | 🔲 Pending | 🔲 Pending | Backend Dev | 0.5
115 | GET /notifications/settings | S | 🟢 Medium | 🔲 Pending | 🔲 Pending | 🔲 Pending | Backend Dev | 0.5
116 | PUT /notifications/settings | S | 🟢 Medium | 🔲 Pending | 🔲 Pending | 🔲 Pending | Backend Dev | 0.5 | quiet hours, toggle types
117 | POST /notifications/device-token — register FCM | S | 🔴 Critical | 🔲 Pending | 🔲 Pending | 🔲 Pending | Backend Dev | 0.5
118 | Firebase FCM integration — push notifications | L | 🔴 Critical | 🔲 Pending | 🔲 Pending | 🔲 Pending | Backend Dev | 2 | Android + iOS + Web
119 | SendPushNotification job (queue-based) | M | 🔴 Critical | 🔲 Pending | 🔲 Pending | 🔲 Pending | Backend Dev | 1
🚨 REPORT MODULE — /api/v1/reports
120 | POST /reports — submit report | M | 🟡 High | 🔲 Pending | 🔲 Pending | 🔲 Pending | Backend Dev | 1 | polymorphic: user/post/comment/room
121 | GET /reports/my — own submitted reports | S | 🟢 Medium | 🔲 Pending | 🔲 Pending | 🔲 Pending | Backend Dev | 0.5
🛡️ ADMIN MODULE — /api/v1/admin
122 | GET /admin/users — list all users | M | 🟡 High | 🔲 Pending | 🔲 Pending | 🔲 Pending | Backend Dev | 1 | super_admin + admin
123 | POST /admin/users/{id}/suspend | S | 🟡 High | 🔲 Pending | 🔲 Pending | 🔲 Pending | Backend Dev | 0.5 | admin + super_admin
124 | POST /admin/users/{id}/ban | S | 🟡 High | 🔲 Pending | 🔲 Pending | 🔲 Pending | Backend Dev | 0.5 | super_admin only
125 | POST /admin/users/{id}/restore | S | 🟡 High | 🔲 Pending | 🔲 Pending | 🔲 Pending | Backend Dev | 0.5
126 | GET /admin/reports — report queue | M | 🟡 High | 🔲 Pending | 🔲 Pending | 🔲 Pending | Backend Dev | 1 | filter by status
127 | POST /admin/reports/{id}/resolve | S | 🟡 High | 🔲 Pending | 🔲 Pending | 🔲 Pending | Backend Dev | 0.5
128 | GET /admin/rooms — active rooms monitor | M | 🟡 High | 🔲 Pending | 🔲 Pending | 🔲 Pending | Backend Dev | 1
129 | POST /admin/rooms/{id}/close — force close | S | 🟡 High | 🔲 Pending | 🔲 Pending | 🔲 Pending | Backend Dev | 0.5
130 | GET /admin/analytics/overview | L | 🟡 High | 🔲 Pending | 🔲 Pending | 🔲 Pending | Backend Dev | 2 | DAU/MAU, revenue, calls
131 | Admin account management (super_admin) | M | 🟡 High | 🔲 Pending | 🔲 Pending | 🔲 Pending | Backend Dev | 1 | create/edit/delete admins
132 | Audit log for all admin actions | M | 🟡 High | 🔲 Pending | 🔲 Pending | 🔲 Pending | Backend Dev | 1 | mandatory
🧪 TESTING & QA
133 | Feature tests: Auth module | M | 🔴 Critical | 🔲 Pending | 🔲 Pending | 🔲 Pending | QA / Backend | 1
134 | Feature tests: Chat module | M | 🔴 Critical | 🔲 Pending | 🔲 Pending | 🔲 Pending | QA / Backend | 1
135 | Feature tests: Call / Video modules | M | 🔴 Critical | 🔲 Pending | 🔲 Pending | 🔲 Pending | QA / Backend | 1
136 | Unit tests: MatchingService | M | 🟡 High | 🔲 Pending | 🔲 Pending | 🔲 Pending | QA / Backend | 1
137 | Unit tests: TranslationService | M | 🟡 High | 🔲 Pending | 🔲 Pending | 🔲 Pending | QA / Backend | 1
138 | Load testing (Locust / k6) | L | 🟡 High | 🔲 Pending | 🔲 Pending | 🔲 Pending | QA | 2 | chat + calls under load
139 | Security / penetration testing | L | 🔴 Critical | 🔲 Pending | 🔲 Pending | 🔲 Pending | Security Eng | 3 | JWT, SQL injection, rate limit
140 | API documentation (Swagger / Postman collection) | M | 🟡 High | 🔲 Pending | 🔲 Pending | 🔲 Pending | Backend Dev | 2

## 🖥️ Frontend Dashboard
🌍 TALKIN — FRONTEND DASHBOARD WORKMAP
React + TypeScript Web App ¦ Frontend Engineer Tracker ¦ Talkin Platform v1.0
STATUS LEGEND → ✅ Done 🔄 In Progress 🔲 Pending ⛔ Blocked 🧪 Testing 🚀 Deployed SIZE → S = Small (<4h) M = Medium (1d) L = Large (2-3d) XL = Extra Large (4+d)
# | Task / Endpoint | Size | Priority | Dev Status | Test Status | Git Upload | Assigned To | Est. Days | Notes
⚙️ PROJECT SETUP
1 | Vite + React 18 + TypeScript init | S | 🔴 Critical | ✅ Done | ✅ Done | ✅ Done | Frontend Dev | 0.5
2 | Tailwind CSS + design tokens setup | S | 🔴 Critical | ✅ Done | ✅ Done | ✅ Done | Frontend Dev | 0.5
3 | Axios client + interceptors (JWT attach) | S | 🔴 Critical | ✅ Done | ✅ Done | ✅ Done | Frontend Dev | 0.5
4 | Zustand store structure | S | 🔴 Critical | 🔲 Pending | 🔲 Pending | 🔲 Pending | Frontend Dev | 0.5 | auth, chat, notifications
5 | React Router v6 routes config | S | 🔴 Critical | 🔲 Pending | 🔲 Pending | 🔲 Pending | Frontend Dev | 0.5
6 | Socket.io client setup | M | 🔴 Critical | 🔲 Pending | 🔲 Pending | 🔲 Pending | Frontend Dev | 1
7 | Environment config (.env.example) | S | 🟡 High | ✅ Done | ✅ Done | ✅ Done | Frontend Dev | 0.5
8 | TypeScript types: user, message, post, call, gift | M | 🔴 Critical | 🔲 Pending | 🔲 Pending | 🔲 Pending | Frontend Dev | 1
9 | Shared components: Avatar, Button, Modal, Toast, Loader | M | 🟡 High | 🔲 Pending | 🔲 Pending | 🔲 Pending | Frontend Dev | 1
🔐 AUTH PAGES
10 | Login page — email + password form | M | 🔴 Critical | 🔄 In Progress | 🔲 Pending | 🔲 Pending | Frontend Dev | 1
11 | Register page — multi-step onboarding | L | 🔴 Critical | 🔲 Pending | 🔲 Pending | 🔲 Pending | Frontend Dev | 2 | language selection step
12 | Forgot password page | S | 🟡 High | 🔲 Pending | 🔲 Pending | 🔲 Pending | Frontend Dev | 0.5
13 | Reset password page | S | 🟡 High | 🔲 Pending | 🔲 Pending | 🔲 Pending | Frontend Dev | 0.5
14 | Email verification redirect handler | S | 🟡 High | 🔲 Pending | 🔲 Pending | 🔲 Pending | Frontend Dev | 0.5
15 | Google OAuth button + flow | M | 🟡 High | 🔲 Pending | 🔲 Pending | 🔲 Pending | Frontend Dev | 1
16 | Auth guard (protected routes) | S | 🔴 Critical | 🔲 Pending | 🔲 Pending | 🔲 Pending | Frontend Dev | 0.5
17 | useAuth hook | S | 🔴 Critical | 🔲 Pending | 🔲 Pending | 🔲 Pending | Frontend Dev | 0.5
👤 PROFILE PAGES
18 | Own profile page — view | M | 🔴 Critical | 🔲 Pending | 🔲 Pending | 🔲 Pending | Frontend Dev | 1
19 | Profile edit form — bio, avatar, country | M | 🔴 Critical | 🔲 Pending | 🔲 Pending | 🔲 Pending | Frontend Dev | 1
20 | Avatar upload + crop UI | M | 🟡 High | 🔲 Pending | 🔲 Pending | 🔲 Pending | Frontend Dev | 1
21 | Language settings panel | M | 🔴 Critical | 🔲 Pending | 🔲 Pending | 🔲 Pending | Frontend Dev | 1 | native + learning, proficiency
22 | Cultural interests selector | M | 🟡 High | 🔲 Pending | 🔲 Pending | 🔲 Pending | Frontend Dev | 1 | onboarding + settings
23 | Public user profile view | M | 🟡 High | 🔲 Pending | 🔲 Pending | 🔲 Pending | Frontend Dev | 1 | follow/unfollow button
24 | Followers / Following lists | S | 🟢 Medium | 🔲 Pending | 🔲 Pending | 🔲 Pending | Frontend Dev | 0.5
💬 CHAT MODULE
25 | Conversation list (left panel) | M | 🔴 Critical | 🔲 Pending | 🔲 Pending | 🔲 Pending | Frontend Dev | 1 | search, unread badge
26 | ChatWindow component — messages panel | L | 🔴 Critical | 🔲 Pending | 🔲 Pending | 🔲 Pending | Frontend Dev | 3 | infinite scroll upward
27 | MessageBubble — text/image/video/audio/gift | L | 🔴 Critical | 🔲 Pending | 🔲 Pending | 🔲 Pending | Frontend Dev | 2 | sent/delivered/seen ticks
28 | TranslationBadge — show translated / original toggle | M | 🔴 Critical | 🔲 Pending | 🔲 Pending | 🔲 Pending | Frontend Dev | 1
29 | MessageInput — text, emoji picker, media attach | L | 🔴 Critical | 🔲 Pending | 🔲 Pending | 🔲 Pending | Frontend Dev | 2
30 | Typing indicator | S | 🟡 High | 🔲 Pending | 🔲 Pending | 🔲 Pending | Frontend Dev | 0.5 | WebSocket
31 | Real-time message delivery (Socket.io) | L | 🔴 Critical | 🔲 Pending | 🔲 Pending | 🔲 Pending | Frontend Dev | 2 | useWebSocket hook
32 | Group chat creation UI | M | 🟡 High | 🔲 Pending | 🔲 Pending | 🔲 Pending | Frontend Dev | 1
33 | Message reply / thread UI | M | 🟢 Medium | 🔲 Pending | 🔲 Pending | 🔲 Pending | Frontend Dev | 1
34 | Block / report user from chat | S | 🟡 High | 🔲 Pending | 🔲 Pending | 🔲 Pending | Frontend Dev | 0.5
📞 AUDIO & VIDEO CALLS
35 | Incoming call overlay / alert | L | 🔴 Critical | 🔲 Pending | 🔲 Pending | 🔲 Pending | Frontend Dev | 2 | ring animation, accept/decline
36 | AudioCall screen — active call UI | L | 🔴 Critical | 🔲 Pending | 🔲 Pending | 🔲 Pending | Frontend Dev | 2 | mute, speaker, end call, timer
37 | VideoCall screen — video grid | L | 🔴 Critical | 🔲 Pending | 🔲 Pending | 🔲 Pending | Frontend Dev | 3 | camera switch, mute, end
38 | WebRTC logic: offer/answer/ICE (useWebRTC hook) | XL | 🔴 Critical | 🔲 Pending | 🔲 Pending | 🔲 Pending | Frontend Dev | 4 | STUN/TURN config, P2P setup
39 | Call history page | S | 🟢 Medium | 🔲 Pending | 🔲 Pending | 🔲 Pending | Frontend Dev | 0.5
40 | Call controls: mute, camera toggle, end button | M | 🔴 Critical | 🔲 Pending | 🔲 Pending | 🔲 Pending | Frontend Dev | 1
🎙️ VOICE ROOMS
41 | Room list / browse page | M | 🔴 Critical | 🔲 Pending | 🔲 Pending | 🔲 Pending | Frontend Dev | 1 | filter by language, mode
42 | Room detail / live room UI | XL | 🔴 Critical | 🔲 Pending | 🔲 Pending | 🔲 Pending | Frontend Dev | 4 | speaker grid, audience list
43 | RoomParticipants panel — roles display | M | 🔴 Critical | 🔲 Pending | 🔲 Pending | 🔲 Pending | Frontend Dev | 1 | host/cohost/speaker/audience icons
44 | RoomControls — mute, raise hand, leave, reactions | L | 🔴 Critical | 🔲 Pending | 🔲 Pending | 🔲 Pending | Frontend Dev | 2
45 | Host controls panel — promote, demote, kick, close | L | 🟡 High | 🔲 Pending | 🔲 Pending | 🔲 Pending | Frontend Dev | 2
46 | Live emoji reaction animation overlay | M | 🟡 High | 🔲 Pending | 🔲 Pending | 🔲 Pending | Frontend Dev | 1 | floating emojis
47 | Create room modal | M | 🟡 High | 🔲 Pending | 🔲 Pending | 🔲 Pending | Frontend Dev | 1
📰 SOCIAL FEED
48 | Feed page — infinite scroll | L | 🔴 Critical | 🔲 Pending | 🔲 Pending | 🔲 Pending | Frontend Dev | 2 | photo + video posts
49 | FeedPost card component | M | 🔴 Critical | 🔲 Pending | 🔲 Pending | 🔲 Pending | Frontend Dev | 1 | like, comment, share, translate
50 | Create post modal — text/photo/video | L | 🟡 High | 🔲 Pending | 🔲 Pending | 🔲 Pending | Frontend Dev | 2 | media upload, drag-drop
51 | Post detail page — comments thread | M | 🟡 High | 🔲 Pending | 🔲 Pending | 🔲 Pending | Frontend Dev | 1
52 | PostComments component — nested list | M | 🟡 High | 🔲 Pending | 🔲 Pending | 🔲 Pending | Frontend Dev | 1
53 | Country-based topics section | M | 🟡 High | 🔲 Pending | 🔲 Pending | 🔲 Pending | Frontend Dev | 1 | group posts by country flag
54 | Saved posts page | S | 🟢 Medium | 🔲 Pending | 🔲 Pending | 🔲 Pending | Frontend Dev | 0.5
55 | Post translation toggle (in-feed) | M | 🔴 Critical | 🔲 Pending | 🔲 Pending | 🔲 Pending | Frontend Dev | 1
🎁 GIFT SYSTEM
56 | GiftPicker modal — catalog grid | M | 🟡 High | 🔲 Pending | 🔲 Pending | 🔲 Pending | Frontend Dev | 1 | cultural category filter
57 | GiftAnimation overlay — plays on receive | L | 🟡 High | 🔲 Pending | 🔲 Pending | 🔲 Pending | Frontend Dev | 2 | CSS/Lottie animation
58 | Coin balance display | S | 🟡 High | 🔲 Pending | 🔲 Pending | 🔲 Pending | Frontend Dev | 0.5 | header/wallet widget
59 | Coin shop page — purchase bundles | M | 🟡 High | 🔲 Pending | 🔲 Pending | 🔲 Pending | Frontend Dev | 1
60 | Gift history page | S | 🟢 Medium | 🔲 Pending | 🔲 Pending | 🔲 Pending | Frontend Dev | 0.5
61 | Gift leaderboard page | S | 🟢 Medium | 🔲 Pending | 🔲 Pending | 🔲 Pending | Frontend Dev | 0.5
🤝 PARTNER MATCHING
62 | Matching preferences page | M | 🟡 High | 🔲 Pending | 🔲 Pending | 🔲 Pending | Frontend Dev | 1 | language goals, cultural interests
63 | MatchCard component — profile summary | M | 🟡 High | 🔲 Pending | 🔲 Pending | 🔲 Pending | Frontend Dev | 1 | score, languages, interests
64 | MatchList — swipe/accept/decline UI | L | 🟡 High | 🔲 Pending | 🔲 Pending | 🔲 Pending | Frontend Dev | 2
65 | Active matches list | S | 🟢 Medium | 🔲 Pending | 🔲 Pending | 🔲 Pending | Frontend Dev | 0.5
🔔 NOTIFICATIONS
66 | Notification center panel / dropdown | M | 🟡 High | 🔲 Pending | 🔲 Pending | 🔲 Pending | Frontend Dev | 1 | unread badge, mark read
67 | Real-time notification delivery (WebSocket) | M | 🔴 Critical | 🔲 Pending | 🔲 Pending | 🔲 Pending | Frontend Dev | 1 | useNotifications hook
68 | Notification settings page — toggle types | S | 🟢 Medium | 🔲 Pending | 🔲 Pending | 🔲 Pending | Frontend Dev | 0.5
69 | Toast notification component — ephemeral alerts | S | 🟡 High | 🔲 Pending | 🔲 Pending | 🔲 Pending | Frontend Dev | 0.5
🛡️ ADMIN PANEL (Super Admin + Admin)
70 | Admin layout — sidebar + role-aware nav | M | 🟡 High | 🔲 Pending | 🔲 Pending | 🔲 Pending | Frontend Dev | 1 | hide sections by role
71 | Admin overview dashboard — metrics + charts | L | 🟡 High | 🔲 Pending | 🔲 Pending | 🔲 Pending | Frontend Dev | 2 | recharts / chart.js
72 | User management table — search, filter, actions | L | 🟡 High | 🔲 Pending | 🔲 Pending | 🔲 Pending | Frontend Dev | 2 | ban/suspend/restore
73 | Report queue — list + resolve actions | M | 🟡 High | 🔲 Pending | 🔲 Pending | 🔲 Pending | Frontend Dev | 1
74 | Voice room monitor — live list + force-close | M | 🟡 High | 🔲 Pending | 🔲 Pending | 🔲 Pending | Frontend Dev | 1
75 | Analytics charts — users, revenue, calls, languages | L | 🟡 High | 🔲 Pending | 🔲 Pending | 🔲 Pending | Frontend Dev | 2
76 | Gift management CRUD (super_admin only) | M | 🟡 High | 🔲 Pending | 🔲 Pending | 🔲 Pending | Frontend Dev | 1
77 | Admin account management (super_admin only) | M | 🟡 High | 🔲 Pending | 🔲 Pending | 🔲 Pending | Frontend Dev | 1 | create / permissions
78 | Admin access matrix enforcement in UI | M | 🟡 High | 🔲 Pending | 🔲 Pending | 🔲 Pending | Frontend Dev | 1 | hide/disable by role
🧪 TESTING & QA
79 | Unit tests: components (Vitest + RTL) | M | 🟡 High | 🔲 Pending | 🔲 Pending | 🔲 Pending | QA / Frontend | 2
80 | E2E tests: auth + chat flow (Playwright) | L | 🟡 High | 🔲 Pending | 🔲 Pending | 🔲 Pending | QA / Frontend | 3
81 | WebRTC call E2E test | L | 🔴 Critical | 🔲 Pending | 🔲 Pending | 🔲 Pending | QA / Frontend | 2
82 | Cross-browser testing (Chrome, Firefox, Safari) | M | 🟡 High | 🔲 Pending | 🔲 Pending | 🔲 Pending | QA | 1
83 | Responsive / mobile breakpoint QA | M | 🟡 High | 🔲 Pending | 🔲 Pending | 🔲 Pending | QA | 1
84 | Accessibility audit (WCAG 2.1 AA) | M | 🟢 Medium | 🔲 Pending | 🔲 Pending | 🔲 Pending | QA | 1
85 | Performance audit (Lighthouse) | M | 🟢 Medium | 🔲 Pending | 🔲 Pending | 🔲 Pending | QA | 1

## 📱 APK Dev (Flutter)
🌍 TALKIN — APK DEVELOPMENT WORKMAP
Flutter Mobile App ¦ Android + iOS ¦ Mobile Engineer Tracker ¦ Talkin Platform v1.0
STATUS LEGEND → ✅ Done 🔄 In Progress 🔲 Pending ⛔ Blocked 🧪 Testing 🚀 Deployed SIZE → S = Small (<4h) M = Medium (1d) L = Large (2-3d) XL = Extra Large (4+d)
# | Task / Endpoint | Size | Priority | Dev Status | Test Status | Git Upload | Assigned To | Est. Days | Notes
⚙️ PROJECT SETUP
1 | Flutter project init (Dart 3.x) | S | 🔴 Critical | ✅ Done | ✅ Done | ✅ Done | Mobile Dev | 0.5
2 | Android + iOS config (bundle ID, permissions) | M | 🔴 Critical | ✅ Done | ✅ Done | ✅ Done | Mobile Dev | 1 | mic, camera, notifications
3 | Dio HTTP client + JWT interceptor | S | 🔴 Critical | ✅ Done | ✅ Done | ✅ Done | Mobile Dev | 0.5
4 | GoRouter navigation setup | S | 🔴 Critical | 🔲 Pending | 🔲 Pending | 🔲 Pending | Mobile Dev | 0.5
5 | Riverpod state management setup | S | 🔴 Critical | 🔲 Pending | 🔲 Pending | 🔲 Pending | Mobile Dev | 0.5
6 | App theme (colors, fonts, dark mode) | M | 🟡 High | 🔲 Pending | 🔲 Pending | 🔲 Pending | Mobile Dev | 1
7 | Environment config (.env) | S | 🟡 High | ✅ Done | ✅ Done | ✅ Done | Mobile Dev | 0.5
8 | Core models: user.dart, message.dart, post.dart… | M | 🔴 Critical | 🔲 Pending | 🔲 Pending | 🔲 Pending | Mobile Dev | 1 | fromJson / toJson
9 | Error handling + API response parser | S | 🔴 Critical | 🔲 Pending | 🔲 Pending | 🔲 Pending | Mobile Dev | 0.5
10 | Hive local storage setup (offline cache) | M | 🟡 High | 🔲 Pending | 🔲 Pending | 🔲 Pending | Mobile Dev | 1
🔐 AUTH SCREENS
11 | Splash screen | S | 🔴 Critical | 🔲 Pending | 🔲 Pending | 🔲 Pending | Mobile Dev | 0.5
12 | Login screen — email + password | M | 🔴 Critical | 🔄 In Progress | 🔲 Pending | 🔲 Pending | Mobile Dev | 1
13 | Register screen — multi-step | L | 🔴 Critical | 🔲 Pending | 🔲 Pending | 🔲 Pending | Mobile Dev | 2 | language + cultural interests step
14 | Forgot password screen | S | 🟡 High | 🔲 Pending | 🔲 Pending | 🔲 Pending | Mobile Dev | 0.5
15 | Email verify waiting screen | S | 🟡 High | 🔲 Pending | 🔲 Pending | 🔲 Pending | Mobile Dev | 0.5
16 | Google Sign-In button | M | 🟡 High | 🔲 Pending | 🔲 Pending | 🔲 Pending | Mobile Dev | 1
17 | Auth provider (Riverpod) | S | 🔴 Critical | 🔲 Pending | 🔲 Pending | 🔲 Pending | Mobile Dev | 0.5 | token persist in SharedPreferences
👤 PROFILE SCREENS
18 | Own profile screen | M | 🔴 Critical | 🔲 Pending | 🔲 Pending | 🔲 Pending | Mobile Dev | 1
19 | Edit profile screen — bio, avatar, country | M | 🔴 Critical | 🔲 Pending | 🔲 Pending | 🔲 Pending | Mobile Dev | 1
20 | Avatar image picker + upload | M | 🟡 High | 🔲 Pending | 🔲 Pending | 🔲 Pending | Mobile Dev | 1 | image_picker + crop
21 | Language settings screen | M | 🔴 Critical | 🔲 Pending | 🔲 Pending | 🔲 Pending | Mobile Dev | 1 | native/learning, proficiency
22 | Cultural interests multi-select screen | M | 🟡 High | 🔲 Pending | 🔲 Pending | 🔲 Pending | Mobile Dev | 1 | flag icons grid
23 | Language badges widget (in profile) | S | 🟡 High | 🔲 Pending | 🔲 Pending | 🔲 Pending | Mobile Dev | 0.5
24 | Public user profile screen | M | 🟡 High | 🔲 Pending | 🔲 Pending | 🔲 Pending | Mobile Dev | 1 | follow/unfollow/gift/chat buttons
💬 CHAT SCREENS
25 | Chat list screen — conversations | M | 🔴 Critical | 🔲 Pending | 🔲 Pending | 🔲 Pending | Mobile Dev | 1 | unread badge, search
26 | Chat detail screen — messages list | L | 🔴 Critical | 🔲 Pending | 🔲 Pending | 🔲 Pending | Mobile Dev | 3 | reverse ListView
27 | MessageBubble widget — text/image/video/audio/gift | L | 🔴 Critical | 🔲 Pending | 🔲 Pending | 🔲 Pending | Mobile Dev | 2 | status ticks
28 | Message translation toggle in bubble | M | 🔴 Critical | 🔲 Pending | 🔲 Pending | 🔲 Pending | Mobile Dev | 1 | tap to show original
29 | MessageInput widget — text, emoji, attach, send | L | 🔴 Critical | 🔲 Pending | 🔲 Pending | 🔲 Pending | Mobile Dev | 2
30 | Real-time messaging (socket_service.dart) | L | 🔴 Critical | 🔲 Pending | 🔲 Pending | 🔲 Pending | Mobile Dev | 2 | Socket.io Dart client
31 | Media message send — image/video/audio | M | 🟡 High | 🔲 Pending | 🔲 Pending | 🔲 Pending | Mobile Dev | 1
32 | Message reply support | M | 🟢 Medium | 🔲 Pending | 🔲 Pending | 🔲 Pending | Mobile Dev | 1
33 | Group chat create + manage screen | M | 🟡 High | 🔲 Pending | 🔲 Pending | 🔲 Pending | Mobile Dev | 1
📞 AUDIO & VIDEO CALLS
34 | Incoming call screen (full-screen overlay) | L | 🔴 Critical | 🔲 Pending | 🔲 Pending | 🔲 Pending | Mobile Dev | 2 | ring, accept, decline, caller info
35 | Audio call screen — active call UI | L | 🔴 Critical | 🔲 Pending | 🔲 Pending | 🔲 Pending | Mobile Dev | 2 | mute, speaker, timer, end
36 | Video call screen — camera + self-preview | L | 🔴 Critical | 🔲 Pending | 🔲 Pending | 🔲 Pending | Mobile Dev | 3 | camera switch, mute video
37 | WebRTC service (flutter_webrtc) | XL | 🔴 Critical | 🔲 Pending | 🔲 Pending | 🔲 Pending | Mobile Dev | 4 | offer/answer/ICE, STUN/TURN
38 | Background call handling (Android / iOS) | L | 🔴 Critical | 🔲 Pending | 🔲 Pending | 🔲 Pending | Mobile Dev | 3 | foreground service Android, CallKit iOS
39 | Call history screen | S | 🟢 Medium | 🔲 Pending | 🔲 Pending | 🔲 Pending | Mobile Dev | 0.5
40 | Missed call notification deep link | M | 🔴 Critical | 🔲 Pending | 🔲 Pending | 🔲 Pending | Mobile Dev | 1 | open call screen on tap
🎙️ VOICE ROOMS
41 | Room list / browse screen | M | 🔴 Critical | 🔲 Pending | 🔲 Pending | 🔲 Pending | Mobile Dev | 1 | filter by language
42 | Room screen — live room UI | XL | 🔴 Critical | 🔲 Pending | 🔲 Pending | 🔲 Pending | Mobile Dev | 5 | speaker grid, audience tiles
43 | Room participant tile widget | M | 🔴 Critical | 🔲 Pending | 🔲 Pending | 🔲 Pending | Mobile Dev | 1 | role icon, speaking indicator
44 | Host controls bottom sheet | L | 🟡 High | 🔲 Pending | 🔲 Pending | 🔲 Pending | Mobile Dev | 2 | promote, kick, close room
45 | Raise hand + emoji reaction buttons | M | 🟡 High | 🔲 Pending | 🔲 Pending | 🔲 Pending | Mobile Dev | 1 | floating reaction animation
46 | Create room bottom sheet | M | 🟡 High | 🔲 Pending | 🔲 Pending | 🔲 Pending | Mobile Dev | 1
📰 SOCIAL FEED
47 | Feed screen — infinite scroll (photo + video) | L | 🔴 Critical | 🔲 Pending | 🔲 Pending | 🔲 Pending | Mobile Dev | 2
48 | FeedPost card widget | M | 🔴 Critical | 🔲 Pending | 🔲 Pending | 🔲 Pending | Mobile Dev | 1 | like, comment, share, translate button
49 | Video post auto-play in feed | M | 🟡 High | 🔲 Pending | 🔲 Pending | 🔲 Pending | Mobile Dev | 1 | video_player package
50 | Create post bottom sheet — camera/gallery/text | L | 🟡 High | 🔲 Pending | 🔲 Pending | 🔲 Pending | Mobile Dev | 2
51 | Post detail screen + comments | M | 🟡 High | 🔲 Pending | 🔲 Pending | 🔲 Pending | Mobile Dev | 1
52 | Country-based topics section in feed | M | 🟡 High | 🔲 Pending | 🔲 Pending | 🔲 Pending | Mobile Dev | 1 | horizontal country tabs
53 | Post translation widget (in-feed tap) | M | 🔴 Critical | 🔲 Pending | 🔲 Pending | 🔲 Pending | Mobile Dev | 1
🎁 GIFT SYSTEM
54 | Gift picker bottom sheet — catalog grid | M | 🟡 High | 🔲 Pending | 🔲 Pending | 🔲 Pending | Mobile Dev | 1
55 | Gift animation overlay (Lottie / Rive) | L | 🟡 High | 🔲 Pending | 🔲 Pending | 🔲 Pending | Mobile Dev | 2 | plays full-screen on receive
56 | Coin balance widget (persistent in header) | S | 🟡 High | 🔲 Pending | 🔲 Pending | 🔲 Pending | Mobile Dev | 0.5
57 | Coin shop screen — in-app purchase bundles | L | 🟡 High | 🔲 Pending | 🔲 Pending | 🔲 Pending | Mobile Dev | 2 | in_app_purchase package
58 | Gift history screen | S | 🟢 Medium | 🔲 Pending | 🔲 Pending | 🔲 Pending | Mobile Dev | 0.5
59 | Gift leaderboard screen | S | 🟢 Medium | 🔲 Pending | 🔲 Pending | 🔲 Pending | Mobile Dev | 0.5
🤝 PARTNER MATCHING
60 | Matching preferences screen | M | 🟡 High | 🔲 Pending | 🔲 Pending | 🔲 Pending | Mobile Dev | 1 | language goals, cultural interests
61 | Match card widget — swipeable profile card | L | 🟡 High | 🔲 Pending | 🔲 Pending | 🔲 Pending | Mobile Dev | 2 | score indicator, language badges
62 | Matching screen — suggestion deck | L | 🟡 High | 🔲 Pending | 🔲 Pending | 🔲 Pending | Mobile Dev | 2 | accept / decline swipe
63 | Active matches list screen | S | 🟢 Medium | 🔲 Pending | 🔲 Pending | 🔲 Pending | Mobile Dev | 0.5
🔔 NOTIFICATIONS
64 | Firebase Messaging setup (FCM) | L | 🔴 Critical | 🔲 Pending | 🔲 Pending | 🔲 Pending | Mobile Dev | 2 | Android + iOS
65 | Push notification permission request | S | 🔴 Critical | 🔲 Pending | 🔲 Pending | 🔲 Pending | Mobile Dev | 0.5
66 | In-app notification center screen | M | 🟡 High | 🔲 Pending | 🔲 Pending | 🔲 Pending | Mobile Dev | 1
67 | Notification deep link handling | M | 🔴 Critical | 🔲 Pending | 🔲 Pending | 🔲 Pending | Mobile Dev | 1 | navigate to correct screen on tap
68 | Notification settings screen | S | 🟢 Medium | 🔲 Pending | 🔲 Pending | 🔲 Pending | Mobile Dev | 0.5
69 | Background push handling (foreground service) | M | 🔴 Critical | 🔲 Pending | 🔲 Pending | 🔲 Pending | Mobile Dev | 1 | Android only
📚 LANGUAGE LEARNING
70 | Learning home screen — progress overview | M | 🟢 Medium | 🔲 Pending | 🔲 Pending | 🔲 Pending | Mobile Dev | 1
71 | Grammar lessons list + detail viewer | M | 🟢 Medium | 🔲 Pending | 🔲 Pending | 🔲 Pending | Mobile Dev | 1
72 | Vocabulary flashcard screen (spaced repetition) | L | 🟢 Medium | 🔲 Pending | 🔲 Pending | 🔲 Pending | Mobile Dev | 2 | flip animation
73 | Daily challenge screen + streak tracker | M | 🟢 Medium | 🔲 Pending | 🔲 Pending | 🔲 Pending | Mobile Dev | 1
74 | Pronunciation guide — audio playback | M | 🟢 Medium | 🔲 Pending | 🔲 Pending | 🔲 Pending | Mobile Dev | 1 | audioplayers package
🏗️ BUILD & RELEASE
75 | Android release build (APK + AAB) | M | 🔴 Critical | 🔲 Pending | 🔲 Pending | 🔲 Pending | Mobile Dev | 1 | signing config, proguard
76 | iOS release build (IPA) | M | 🔴 Critical | 🔲 Pending | 🔲 Pending | 🔲 Pending | Mobile Dev | 1 | Xcode archive, provisioning profile
77 | Google Play Store listing | M | 🟡 High | 🔲 Pending | 🔲 Pending | 🔲 Pending | Mobile Dev | 1 | screenshots, description, privacy policy
78 | Apple App Store listing | M | 🟡 High | 🔲 Pending | 🔲 Pending | 🔲 Pending | Mobile Dev | 1
79 | Firebase App Distribution (beta testers) | S | 🟡 High | 🔲 Pending | 🔲 Pending | 🔲 Pending | Mobile Dev | 0.5
80 | Crash reporting: Firebase Crashlytics | S | 🟡 High | 🔲 Pending | 🔲 Pending | 🔲 Pending | Mobile Dev | 0.5
🧪 TESTING & QA
81 | Unit tests: providers, services | M | 🟡 High | 🔲 Pending | 🔲 Pending | 🔲 Pending | QA / Mobile | 1
82 | Widget tests: key components | M | 🟡 High | 🔲 Pending | 🔲 Pending | 🔲 Pending | QA / Mobile | 1
83 | Integration tests: auth + chat + call flow | L | 🔴 Critical | 🔲 Pending | 🔲 Pending | 🔲 Pending | QA / Mobile | 2
84 | Android device farm testing (Firebase Test Lab) | L | 🟡 High | 🔲 Pending | 🔲 Pending | 🔲 Pending | QA | 2
85 | iOS device testing (iPhone 14, 15, SE) | L | 🟡 High | 🔲 Pending | 🔲 Pending | 🔲 Pending | QA | 2
86 | Performance profiling (Flutter DevTools) | M | 🟢 Medium | 🔲 Pending | 🔲 Pending | 🔲 Pending | QA | 1